## Feb
Time | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | [6 empty] | 8 | 136
| 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28
| M | T | O | T | F |  |  | M | T | O | T | F |  |  | M | T | O | T | F |  |  | M | T | O | T | F |  |  | M
Planning | 2022-02-16: Daily 5; 2022-02-17: Daily 5; 2022-02-18: Daily 5; 2022-02-21: Daily 5; 2022-02-22: Daily 5; 2022-02-23: Daily 5; 2022-02-24: Daily 5; 2022-02-25: Daily 5; 2022-02-28: Daily 5
Architecture | bar: 2022-01-31 to 2022-02-03
**Clean architecture | bar: 2022-02-01 to 2022-02-04
**MediatR pattern | bar: 2022-02-01 to 2022-02-04
Basic Functions | bar: 2022-02-04; 2022-02-07 to 2022-02-11
Create/Read Manager/Update | bar: 2022-02-11
Create/Read Team | bar: 2022-02-10 to 2022-02-11
Create/Read Player | bar: 2022-02-09
Create/Read League
Create/Read Fixtures | bar: 2022-02-09; 2022-02-16 to 2022-02-17; 2022-02-28
*Database - Code First | bar: 2022-02-02 to 2022-02-04
**Manager | bar: 2022-02-03 to 2022-02-04
**Player | bar: 2022-02-03 to 2022-02-04
**Team | bar: 2022-02-03 to 2022-02-04
**League ?
**Fixtures | bar: 2022-02-15 to 2022-02-16
**Webscrape Player data (UiPath) | bar: 2022-02-07
** Import Player data Excel -> Sql | bar: 2022-02-07
** Redefine Player tables | bar: 2022-02-07
*** FullName -> FirstName, LastName | bar: 2022-02-07
** Webscrape Team data (UiPath) | bar: 2022-02-11
** Import Team data Excel -> Sql | bar: 2022-02-14
** Redefine Team tables | bar: 2022-02-14
Game Functions
* Start game (Create Manager, Choose Team) | bar: 2022-02-21
* Play through game
** Calc game results
* Show results
* List/Update League
* Calculate Fixtures | bar: 2022-02-28
Tests

## Mars
Time | 8 | 8 | 8 | 8 |  | 8 | [25 empty] | 40
| 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31
| T | O | T | F | L | S | M | T | O | T | F | L | S | M | T | O | T | F |  |  | M | T | O | T | F |  |  | M | T | O | T
Create/Read League | bar: 2022-03-13 to 2022-03-14
Create/Read/Update Fixtures | bar: 2022-03-03 to 2022-03-04
*Database - Code First
**Manager
**Player
**Team
**League ? | bar: 2022-03-13 to 2022-03-14
**Fixtures
**Webscrape Player data (UiPath)
** Import Player data Excel -> Sql
** Redefine Player tables
*** FullName -> FirstName, LastName
** Webscrape Team data (UiPath)
** Import Team data Excel -> Sql
** Redefine Team tables
Game Functions
* Start game (Create Manager, Choose Team) | bar: 2022-03-01 to 2022-03-02
* Play through game | bar: 2022-03-13 to 2022-03-14
** Calc game results | bar: 2022-03-13 to 2022-03-14
* Show results | bar: 2022-03-14 to 2022-03-15
* List/Update League | bar: 2022-03-14 to 2022-03-15
* Calculate Fixtures | bar: 2022-03-03 to 2022-03-04
Show Main Menu | bar: 2022-03-06; 2022-03-13 to 2022-03-14
Show menu 1 - Sell/Print players skeleton | bar: 2022-03-13 to 2022-03-14
Show menu 2 - Print score skeleton | bar: 2022-03-14
Show menu 5 - Display League table skeleton | bar: 2022-03-14
Setup ManagedTeam | bar: 2022-03-13

## April
2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30
F |  |  | M | T | O | T | F |  |  | M | T | O | T | F |  |  | M | T | O | T | F |  |  | M | T | O | T | F

## Tests
| Test/Function | Impl. Date | Pass
UT001 | Calc fixtures
UT002 | Calc match results
UT003 | Match Win
UT004 | Match Draw
UT005 | Match Lost
UT006 | Goal Home Team | 2022-02-23
UT007 | Goal Away Team | 2022-02-23
UT008 | Display League table
UT009 | Display Match
UT010

## Blad1
Tidrapport
Datum | Start | Slut | Längd | Uppgift
2022-03-11 | 9:00 | 10:00 | 1:00 | Utbildning Agil projektledning
| 10:00 | 10:15 | 0:15 | Jobbsök/Uppföljning - Agio
| 10:15 | 10:20 | 0:05 | Excelfix tidrapport
| 10:20 | 11:00 | 0:40 | LinkedIn, Github fix
| 11:00 | 12:00 | 1:00 | Utbildning Agil projektledning
| 12:00 | 13:45 | 1:45 | Lunch
| 13:45 | 14:10 | 0:25 | Nyheter, C#
| 14:10 | 15:00 | 0:50 | Utbildning Agil projektledning
Misc Total |  |  | 1:45
Jobbsök aktiviteter |  |  | 4:15
Total dev |  |  | 0:00
Datum | Start | Slut | Längd | Uppgift
2022-03-13 | 10:00 | 12:00 | 2:00 | Setting up menu structure
| 12:00 | 13:00 | 1:00 | FBM setup team with players
Misc | 13:00 | 16:00 | 3:00 | Ute Vindskivor
| 16:00 | 19:00 | 3:00 | FBM setup team with players
Misc | 19:00 | 21:00 | 2:00 | Rekreation
Misc Total |  |  | 5:00
Total dev |  |  | 6:00
Datum | Start | Slut | Längd | Uppgift
2022-03-14 | 8:00 | 10:00 | 2:00 | Funct to copy Team Id to db table Players
| 10:00 | 10:15 | 0:15 | Excel fix
| 10:15 | 10:30 | 0:15 | Paus
| 10:30 | 11:30 | 1:00 | Error in GetPlayerByTeamName
| 11:30 | 14:30 | 3:00 | handla, lunch
| 14:30 | 17:15 | 2:45 | Rekreation
| 17:15 | 19:00 | 1:45 | Error in Player API
| 19:00 | 21:30 | 2:30 | Fix Manager + Player Update
Misc Total |  |  | 6:00
Jobbsök aktiviteter
Total dev |  |  | 7:30
Datum | Start | Slut | Längd | Uppgift
2022-03-15 | 8:00 | 9:40 | 1:40 | fix Manager + Player Update API call
| 9:40 | 10:00 | 0:20 | Paus
| 9:40 | 11:00 | 1:20 | Curonova möte
| 12:00 | 13:00 | 1:00 | Lunch
| 13:00 | 14:45 | 1:45 | Update error 500 from frontend
| 14:45 | 16:00 | 1:15 | Jobbsök
| 16:00 | 17:45 | 1:45 | Middag
| 17:45 | 21:00 | 3:15 | fix all new Player Update API call, now working!
|  |  | 0:00 | changed to a completely new function
Misc Total |  |  | 3:05
Jobbsök aktiviteter |  |  | 2:35
Total dev |  |  | 6:40
Datum | Start | Slut | Längd | Uppgift
2022-03-16 | 8:00 | 8:00 | 0:00 | Huvudvärk
| 8:00 | 8:00 | 0:00
| 12:00 | 14:30 | 2:30 | Lunch
| 14:30 | 16:00 | 1:30 | fix start of game functions(intit manager, team etc.)
| 16:00 | 17:20 | 1:20
| 17:20 | 19:00 | 1:40 | fix start of game functions(intit manager, team etc.)
| 19:00 | 19:00 | 0:00
| 19:00 | 19:00 | 0:00
Misc Total |  |  | 3:50
Jobbsök aktiviteter
Total dev |  |  | 3:10
Datum | Start | Slut | Längd | Uppgift
2022-03-17 | 9:00 | 10:30 | 1:30 | Networking, LinkedIn, mails etc.
| 10:30 | 11:30 | 1:00 | read up on Unit testing with xUnit
| 11:30 | 13:00 | 1:30 | Lunch
| 13:00 | 14:30 | 1:30 | Jobbsök
| 14:30 | 16:30 | 2:00 | read up on Unit testing with xUnit (Pluralsight)
| 16:30 | 16:45 | 0:15 | Paus
| 16:45 | 18:15 | 1:30 | create new tests
| 18:15 | 19:15 | 1:00 | Middag + vila
| 19:15 | 21:30 | 2:15
Misc Total |  |  | 2:45
Jobbsök aktiviteter |  |  | 3:00
Total dev |  |  | 6:45
Datum | Start | Slut | Längd | Uppgift
2022-03-18 | 8:00 | 10:00 | 2:00
| 10:00 | 10:00 | 0:00
| 12:00 | 13:00 | 1:00 | Lunch
| 13:00 | 13:00 | 0:00
| 13:00 | 13:00 | 0:00
| 13:00 | 13:00 | 0:00
| 13:00 | 13:00 | 0:00
| 13:00 | 13:00 | 0:00
Misc Total |  |  | 1:00
Jobbsök aktiviteter
Total dev |  |  | 2:00